## WBS
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Background Verification System | 1 | Analysis | Requirement Analysis | 1 | 2019-08-07 | 2019-08-07 | 1 | 2019-08-07 | 2019-08-07 | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Preparing understanding document | 1 | 2019-08-07 | 2019-08-07 | 1 | 2019-08-07 | 2019-08-07 | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Updating QTS | 1 | 2019-08-07 | 2019-08-07 | 0.5 | 2019-08-07 | 2019-08-07 | Janaki | Completed
|  | Design | Unit Test Plan Preparation | 2 | 2019-08-08 | 2019-08-08 | 2 | 2019-08-08 | 2019-08-08 | Surenderan | Completed
|  |  | LLD Preparation | 3 | 2019-08-08 | 2019-08-08 | 2 | 2019-08-08 | 2019-08-08 | Prakhar | Completed
|  |  | UTP Review | 1 | 2019-08-08 | 2019-08-08 | 1 | 2019-08-08 | 2019-08-08 | Sammanitha | Completed
|  |  | UTP Rework | 1 | 2019-08-08 | 2019-08-08 | 2 | 2019-08-08 | 2019-08-08 | Janaki | Completed
|  |  | LLD Review | 1 | 2019-08-08 | 2019-08-08 | 1 | 2019-08-08 | 2019-08-08 | Vishal | Completed
|  | Build | Coding | 8 | 2019-08-08 | 2019-08-12 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Code Self Review | 2 | 2019-08-12 | 13-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Self Testing | 2 | 2019-08-12 | 13-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Rework |  | 2019-08-12 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Code Peer Review |  | 2019-08-12 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Peer Testing |  | 2019-08-13 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Test Result review |  | 2019-08-13 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Rework |  | 2019-08-13 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Code Integration |  | 14-8-2019 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Integration Testing |  | 14-8-2019 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Rework |  | 14-8-2019 | 14-8-2019 |  |  |  | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Test Result review | [6 empty] | Prakhar,Vishal S,Surenderan,Janaki,Sammanitha | Completed
|  |  | Total Planned Hrs : |  |  | Total Actual Hrs: